How do you evaluate the performance of a project in agile?

The first priority of an agile project is to satify the customer by continuously delivering valuable working software.

The performance of a project in agile is evaluated by:

- Velocity
- Hit rate
- work remaining on tasks
- Project cost

Velocity, helps us to determine the rate at which a team produces a working software. Velocity is measured in terms of number of story points a team can deliver per sprint. It is used for estimation and planning.

Hit rate is the percentage of the work actually completed in a timebox with reference to the work actually allocated during that particular timebox. Hit rate helps to determine the efficiency of the team and helps to create a baseline on which the effficiency of the team will be measured in future.

Work remaining on tasks is the estimates of work remaining calculated each day by agile team with reference to the active tasks. An agile team,in due course of time will try to reduce it’s work remaining on tasks, but if the work in the future is more complicated than it was anticipated,then it will continue to increase and will affect the progress of the project as the team won’t be able to deliver the working software to customer on time.

Project cost: The cost of a project must be tracked to ensure it does not go over budget. Since we track it from the start till the end of the project. In agile, we use to determine the outcome of a project whether it is a success or not on the basis of Earned Business Value rather than Earned Value Management which takes into account the business value of the completed work.

1. Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation

Traditional monitoring and control(TMC)	Agile monitoring and control(AMC)
TMC focuses on how much time has been spent on a particular task.	AMC focuses on what software has been incrementally delivered.
It is concerned with actual performance of project with respect to the plan and fixing it if it varies from the plan(earned value management).	It is concerned with whatever has been produced is of some business value or is of how much value for the customer as the software is delivered on an incremental basis(earned business value).
It measures the output of a project.	It measures the outcomes of the project.
Here the success of the project is measured on the basis of Schedule performance index(SPI) and Cost perfromance index(CPI),if SPI>=1 and CPI>=1,then project is a success	Here the success of the project is measured according the business value perspective,that is the business value of the finished work determines the success or failure of the project. Hence, it helps to measure how much of the value added work has been completed rather than in TMC where there is no difference in the value and non value activity.

With a total project budget of $ 175,000, and having completed one out of four Iterations, we have this product backlog and these actuals:

	Estimate	Completed		Actual Cost (1000s
Feature	(storypoints)	(storypoints)		dollars)

Welcome Screen	10	10		15

Advert - Splash Screen	20	20		30

Login Screen	10	10		20

Personalized Google Ads	20

Catalog Browser	20

Catalog Editor	10

Shopping Basket Browser	5

Shopping Card Editor	25

Check-out Process	20

Invoice Calculation	10

Credit Card Verification	10

PayPal Payment Handling	20

Order Confirmation Email	20

Totals	200	40		65

in our example, after Iteration 1 we should be at 25% complete)

Calculate Planned Value Actual%Completed
Earned Value

Budget at complete(BAC) =$175000
Planned percentage complete=25%
Total no of story points completed=40
total no of story points planned=200

Planned Value(PV)=BAC* Planned percentage completed

     = 25% of 175000 = $ 43750

Actual % completed=total no of story points completed/ total no of story points planned

=20/400=20% completed

Earned Value(EV)=BAC*Actual% completed

      = 20% of 175000= $ 35000